## Slide 1: Overview of the current status and plans for the 2027ab run
Takaaki Yamaguchi
(on behalf of SuperKEKB accelerator team)
2026.10.19 B2GM

## Slide 2: Contents
Summary of 2026ab run
Plans for the 2027ab run
Hardware works during this summer shutdown
  RF
  Vacuum
  Injector

## Slide 3: Brief summary of 2026ab run
Achieved records:
  Max. luminosity (Belle off) : 5.32 x 1034 cm–2 s–1
  Max. luminosity (Belle on) : 5.28 x 1034 cm–2 s–1
  Max. integrated luminosity/day:
    3.499 fb–1 (recorded)
    3.948 fb–1 (delivered)
  Integrated luminosity/2026ab run:
    314.5 fb–1 (recorded)
    361.6 fb–1 (delivered)
  Max. beam current:
    LER: 1.73 A
    HER: 1.37 A
Successful 2-bunch injection to two rings
Physics run with βy* = 0.9 mm
Major hardware issues and related works during this summer shutdown:
  Abnormal vacuum-pressure rise of two RF cavities → Investigation
  Several collimators damaged → Replacement of collimator jaws
  Vacuum leak at beam pipes → Replacements and countermeasures
2026ab run
For the detail of 2026ab run, see the previous B2GM talk by T. Okada (https://indico.belle2.org/event/17880/)

## Slide 4: Plans for the 2027ab run
- Schedule from 2026c to 2027ab
- Actions for L = 1 x 1035 cm–2 s–1

## Slide 5: Schedule (2026c–2027ab)
2026c operation (autumn)
  Linac: Sep. 14–Dec. 24
  DR, BT: Nov. 30–Dec. 24 → Beam tuning/study
  MR: hardware works continue, beam operation is skipped.
2027a operation (former spring period)
  Linac: Jan. 4–Mar. 31
  DR, BT: Jan. 6–Mar. 31
    2–3 weeks for beam tuning/study before MR beam operation starts
  MR: Jan. 25–Mar. 31
2027b operation (latter spring period)
  The baseline plan is to continue the beam operation until the end of May.
  Depending on the budgetary situation, the operation period may be extended.
  However, the machine stability at increasing temperature must be considered.
Sun | Mon | Tue | Wed | Thu | Fri | Sat
1 | 2 | 3 | 4 | 5 | 6 | 7
8 | 9 | 10 | 11 | 12 | 13 | 14
15 | 16 | 17 | 18 | 19 | 20 | 21
22 | 23 | 24 | 25 | 26 | 27 | 28
29 | 30 | 1 | 2 | 3 | 4 | 5
Sun | Mon | Tue | Wed | Thu | Fri | Sat
29 | 30 | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 | 31 | 1 | 2
Sun | Mon | Tue | Wed | Thu | Fri | Sat
27 | 28 | 29 | 30 | 31 | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31 | 1 | 2 | 3 | 4 | 5 | 6
2026c
November
2026c
December
2027a
January
Linac
Linac
Linac
Linac
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac
Linac+BT/DR
Linac+BT/DR
MR
Linac+BT/DR
MR

## Slide 6: Machine parameters for L = 1 x 1035 cm–2 s–1
To reach L = 1 x 1035 cm–2 s–1, we need to
  Achieve high beam currents (LER: 2.6 A, HER 2.0A)
  Keep high beam qualities (specific luminosity, beam lifetime, background, ...)
Key issues:
  High-quality injection (low injection background, high injection efficiency)
  Suppress beam instabilities (sudden beam losses, …)
  Understand/suppress specific luminosity degradation (emittance blow-up, …)
Measured specific luminosity
LER~1.7A + HER~1.3 A (~2000 bunches)
LER~0.42 A + HER~0.32 A (393 bunches)
Mitsuka
2024/12 reached
Main machine parameters
Present target

## Slide 7: Major actions to L = 1 x 1035 cm–2 s–1
High-quality injection
  RF gun replacement → lower emittance
  More precise beam control in Linac/BT under 2-bunch injection:
    Auto-tuning/feedback systems for emittance and beam orbit,
    Beam control using fast kickers,
    Update of beam diagnostic system, …
  Chamber replacement at the LER injection point
Suppress beam instabilities
  Suppression of sudden beam loss (SBL) events (SBL taskforce)
  Countermeasures against HER-unique vertical instabilities
Understand/suppress specific luminosity degradation
  Beam-beam taskforce
  Application of AI?

## Slide 8: Sudden beam loss (SBL)
Overview in 2026ab run:
  LER:
    Occurrence rate was significantly reduced by removing black stain generated by vacuum sealant (VACSEAL) inside beam chambers.
    However, SBL still occurred at high current. → SBL sources still remain in LER?
  HER:
    HER-caused aborts were more than LER-caused ones.
    ~30% of HER beam aborts were caused by a specific vertical beam instability (fast-ion instability?).
Future plans and countermeasures are under discussion in SBL taskforce (K. Uno)
  There are conditioning effects in SBL events of both rings (statistical analyses of SBL-related aborts by T. Abe, K. Uno).
  Introduction of mini bunch gaps is effective to reduce the HER vertical instabilities (confirmed in 2026ab).
Countermeasures & operation plan proposed by SBL TF:
  Vacuum group will investigate the beam pipe insides suspected of SBL sources.
  High current vacuum scrubbing (LER 2.0 A/HER 1.6 A, ~1 week)
  Introduction of mini gaps in 2027ab run
Terui
Black stain found inside a chamber
Beam abort
Vertical beam instability unique in HER (“triangle”-type abort)
1 turn
Vertical beam position
Mini-gap study in 2026ab run
abort gap
mini gaps
Without mini gaps
→ Instability occurred
With mini gaps
→ Instability suppressed
abort gap
For the detail of SBL-related analyses,
see the MDI TF meeting talk by K. Uno (https://kds.kek.jp/event/60798/)

## Slide 9: Hardware works (RF)
Investigations on vacuum-pressure rises in RF cavities

## Slide 10: Vacuum-pressure rises in D05A and D05F cavities
In 2025c–2026ab run, abnormal vacuum-pressure rises occurred at D05A and D05F cavities.
  D05A: Dec. 5, 2025 (during beam operation)
  D05F: Apr. 15, 2026 (during cavity aging on a regular maintenance day)
  → After the vacuum pressure rises, these cavities were detuned (out-of-operation).
Both cavities are the normal-conducting ARES cavities used for LER.
In the 2026 summer shutdown, investigations were conducted by ARES cavity group.
ARES cavity
Beam
A-cavity
S-cavity
C-cavity
Three-coupled-cavity cavity system to suppress coupled-bunch instability caused by accelerating mode
D05
D04
D07
D08
D10
D11
IP
D05A
D05F
Distribution of RF stations
OHO
straight section

## Slide 11: Investigation on cavity pressure rise
  The source of pressure rise was a vacuum leak at the joint between the C- and S-cavity.
  By obscure failure of a flap flow meter, cooling water flow was insufficient at the middle part of the storage cavity. → Large thermal expansion led to vacuum leak at the joint.
  On a regular maintenance day, cooling water leak was found on the top of the storage cavity.
  After partial removal work of cooling water, cavity aging was conducted as usual. → Abnormal vacuum-pressure rise occurred.
  By leak tests and high-power tests in this summer shutdown, vacuum-pressure rise could not be reproduced.
  A possible cause of the pressure rise is that the cooling water channel was not re-open after partial removal work of cooling water.
A-cavity
S-cavity
C-cavity
C-cavity
S-cavity
He gas
Joint between the coupling cavity and storage cavity
Cooling channel to the upper part of S-cavity
Cooling channel to the middle part of S-cavity
Flap flow meters
Water leak
Cooling water leak at D05F cavity
D05-A and -F cavities are normal and will return to operation without cavity replacement.
→ This will contribute to higher beam current!
D05A cavity:
D05F cavity:

## Slide 12: Hardware works (Vacuum)
- Vacuum leak countermeasures
- Replacement of collimator jaws

## Slide 13: Vacuum works (LER)
Wiggler part
  Countermeasures against vacuum leak
    Bellows chambers with reinforced water cooling
    → Reduction of vacuum leak risk at high current
Replacements of the collimator jaws
  D03V4
  D05V1
Replacement of QI6P chamber (injection point)
  Improvement of injection efficiency is expected.
4. QI6P chamber replacement
1. Wiggler-related work
3. Collimator jaw replacement (D05V1)
2. Collimator jaw replacement (D03V4)
LER
Ishibashi
    Bellows chambers with reinforced water cooling
    Damaged collimator jaws (D03V4)
Top
Bottom

## Slide 14: Vacuum works (HER)
HER
2. Collimator jaw replacement (D01V1)
4. Installation of new D09V1
1. Installation of flange for length adjustment at D09V3
3. Install ZVF4RE SUS beam pipe
5. IP FT replacement
Ishibashi
    Damaged collimator jaws (D01V1)
Top
Bottom
Replacement of the collimator jaws
  D01V1
Installation of the new D09V1 collimator with water cooling channel
Repair of ZVF4RE stainless-steel beam pipes
  Large vacuum leak occurred in 2026ab run.
  Fabrication of a new chamber underway

## Slide 15
Hardware works (QCS)
- Adjustment of a cryogenic valve (CV414) experiencing seat leakage
- Adjustment of the QC1RP quench detection voltage to prevent ESR1 from quench

## Slide 16
QCS works
Adjustment of a cryogenic valve (CV414) experiencing seat leakage
  Following a momentary power interruption on June 19, seat leakage occurred at CV414, making it impossible to maintain the liquid helium level used to cool the QCS superconducting magnet. Emergency measures were taken to stop the seat leakage, and accelerator operation continued while maintaining the liquid level.
  The opening of CV414 relative to the commanded value was inspected, and no abnormalities were found. A visual inspection and adjustment of the valve element are scheduled for November.
Adjustment of the QC1RP quench detection voltage to prevent ESR1 from quench
  When massive beam loss occurred at intensities exceeding 0.8 mA/bunch, the quench detection for QC1RP took approximately 17 ms; consequently, heat generation in QC1RP caused ESR1 to quench twice during the 2026ab run.
  To accelerate quench detection and reduce heat generation in the QC1RP, we will attempt to lower the quench detection voltage threshold from the current 1 V to 0.2 V.
Momentary power interruption
Seat leakage
June 19
Liquid helium level continues to drop
17ms
Coil voltages
Emergency measures
LER abort kicker
Quench trigger
Joule heat
QC1RP quench voltages

## Slide 17: Hardware works (Injector)
Installation of a new RF electron gun

## Slide 18: Installation of a new RF gun
The current RF gun was installed in the summer shutdown in 2025.
  Cavity trips were successfully reduced.
  Several troubles occurred in the fabrication process.
To achieve higher RF power, a new RF gun cavity is installed in this summer shutdown.
  Long cavity aging was done without any problems.
  Lower emittance in 2-bunch injection expected.
Yoshida

## Slide 19: Other hardware works
Linac
  Repair of fast kicker power supply
  Replacement of 12 old accelerating structures
BT
  Water quality improvement of magnets
    Prevention of pipe clogging → downtime reduction
  Installation of more magnet thermometers
    Monitor temperature rise caused by water flow reduction
  Update of BPM readout system
    Enables more precise beam control under 2-bunch injection scheme
Injection point
  Replacing the thyratron in the LER injection-kicker power supply with a different type.
    Prevention of accidental kicker fires → downtime reduction
MR
  Installation of more beam loss monitors
  Maintenance of the cooling water system for the ring magnets
    Interlock threshold check, pipe cleaning → downtime reduction
  Measurement of all quadrupole magnet tilts
  Addition of radiation shielding for the magnets downstream of the collimator

## Slide 20: Summary
In 2026ab run, we achieved the stable high current beam operation and updated the luminosity world record.
The hardware works and operation planning are ongoing since the summer shutdown:
  High-quality injection
  Stable/reliable operation
  Suppression of SBL events

## Slide 21: Back-up

## Slide 22: 2027ab Startup Schedule (Proposal)
2026.10.6
Kyo Shibata

## Slide 23: Startup schedule for the 2027ab run
Before the New Year
  Linac operation: 9/14 - 12/24
  BT/DR operation: 11/30 - 12/24
     3 weeks are required for BT/DR tuning in Fuji mode.
      Fuji mode:
        Beam operation only up to the beam dump in the downstream section of the BT.
        Precise beam tuning for MR injection is not possible.
        Half of the MR ring remains accessible.
    Replacement of the LER injection-point chamber is also scheduled.
      BT operation is not possible during the daytime shift.
    BT operation cannot start before Nov. 30 due to maintenance of the BT magnet power supplies.
Sun | Mon | Tue | Wed | Thu | Fri | Sat
29 | 30 | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 | 31 | 1 | 2
Sun | Mon | Tue | Wed | Thu | Fri | Sat
27 | 28 | 29 | 30 | 31 | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31 | 1 | 2 | 3 | 4 | 5 | 6
2026c
December
2027a
January
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac
Linac+BT/DR
Linac+BT/DR
MR
Linac+BT/DR
MR
Linac
LER injection-pint chamber replacement
LER injection-pint chamber replacement
RF startup preparation
Cryogenic system startup
Fuji mode
Fuji mode
Fuji mode
Fuji mode
Beam Shutter mode
Beam Shutter mode
Beam Shutter mode

## Slide 24: Startup schedule for the 2027ab run
After the New Year
  Linac operation: 1/4 -
  BT/DR operation: 1/6 -
     3 weeks are required for BT/DR tuning in Beam Shutter mode.
      Beam Shutter mode:
        Beam operation up to the beam shutter at the downstream end of the BT.
        Precise beam tuning for MR injection is possible.
        MR ring is not accessible.
    RF startup preparation is also scheduled.
      Beam Shutter mode operation must be interrupted.
  MR operation: 1/25 –
    The cryogenic system will be started on Jan. 4.
      No cryogenic operation is required during the winter shutdown (12/29-1/3).
    The earliest possible date for MR startup is Jan. 25.
      Starting the cryogenic system before Jan. 4 would not allow an earlier MR startup.
Proposal: Start MR operation on Jan. 25
  The 2027ab run will continue through the end of May.
Sun | Mon | Tue | Wed | Thu | Fri | Sat
29 | 30 | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 | 31 | 1 | 2
Sun | Mon | Tue | Wed | Thu | Fri | Sat
27 | 28 | 29 | 30 | 31 | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31 | 1 | 2 | 3 | 4 | 5 | 6
2026c
December
2027a
January
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac+BT/DR
Linac
Linac+BT/DR
Linac+BT/DR
MR
Linac+BT/DR
MR
Linac
LER injection-pint chamber replacement
LER injection-pint chamber replacement
RF startup preparation
Cryogenic system startup
Fuji mode
Fuji mode
Fuji mode
Fuji mode
Beam Shutter mode
Beam Shutter mode
Beam Shutter mode

## Slide 25: Vacuum-pressure rises in D05A and D05F cavities
In 2025c–2026ab run, abnormal vacuum-pressure rises occurred at D05A and D05F cavities.
  D05A: Dec. 5, 2025 (during beam operation)
  D05F: Apr. 15, 2026 (during cavity aging on a regular maintenance day)
    On the same day, cooling water leak was found.
  → After the vacuum pressure rises, these cavities were detuned (out-of-operation).
Both cavities are the normal-conducting ARES cavities used the OHO straight section.
In the 2026 summer shutdown, investigations were conducted by ARES cavity group.
ARES cavity
Beam
A-cavity
S-cavity
C-cavity
Three-coupled-cavity cavity system to suppress coupled-bunch instability caused by accelerating mode
D05
D04
D07
D08
D10
D11
IP
D05A
D05F
Distribution of RF stations
OHO
straight section

## Slide 26: D05A cavity
Large vacuum-pressure rise occurred on Dec. 5, 2025 (during beam operation).
During the 2026 summer shutdown, ARES cavity group investigated the source of pressure rise.
  Similar vacuum pressure rise was reproduced due to a vacuum leak at the joint between the C- and S-cavity (confirmed by He leak test)
  The joint is vacuum-sealed by a metal O-ring.
CCG voltage at D05 section around the time
of large vacuum-pressure rise
← 8e–7 Pa
← 5e–3 Pa
A-cavity
S-cavity
C-cavity
C-cavity
S-cavity
He gas
Joint between the coupling cavity and storage cavity
Vacuum-pressure rise observed in the
high-power test conducted
in the summer shutdown
← 2e–3 Pa
← 3e–7 Pa
metal O-ring
Vacuum sealing

## Slide 27: Cause of D05A cavity vacuum leak
By obscure failure of a flap flow meter, cooling water flow was insufficient at the middle part of the storage cavity.
  Thermal expansion led to vacuum leak at the joint.
Cooling channel to the upper part of S-cavity
Cooling channel to the middle part of S-cavity
Flap flow meters
Temperature measured
17 min. after RF turned off
Only this channel is significantly hot!
With the normal cooling water flow, we have confirmed no vacuum leak at the joint during high-power operation with maintaining Vc = 0.5 MV/cavity.

## Slide 28: D05F cavity
On a regular maintenance day (Apr. 15, 2026), cooling water leak was found on the top of the storage cavity.
After partial removal work of cooling water, cavity aging was conducted as usual. → Abnormal vacuum-pressure rise occurred.
Water leak
Frequency tuner
Partial removal
of cooling water
Cooling water including rust inhibitor
(the storage cavity is made from iron)
Vacuum leak during cavity aging
Vac. pressure
RF power
2e–6 Pa →
4e–6 Pa →
5e–6 Pa

## Slide 29: Investigation on D05F cavity
During this summer shutdown, investigation on D05F was conducted parallel with that on D05A.
ARES cavity group first suspected galvanic corrosion between the monitor port (stainless steel) and cavity main part (carbon steel).
They conducted the following tests:
  Cleaning work (Jul. 3, 2026) → Baking of the monitor ports at 80ºC
  Leak test without RF input → no leak found
  Leak test with RF input → no leak found
  Injected acetone and ethanol → leak test → no leak found
  High-power test at the RF voltage of 0.5 MV → no leak
    In the investigation of D05F, the pressure rise could not be reproduced!
  Observed the cavity inside → nothing wrong
Vacuum seal welding
Monitor port
D05F Cavity after cleaning
Solvent injected to the root of the monitor port
Cavity inside investigation

## Slide 30: Summary of investigation on abnormal vacuum-pressure rises
D05A (clear)
  By obscure failure of a flap flow meter, cooling water was insufficient.
  Thermal expansion induced vacuum leak at the joint between the coupling cavity and storage cavity.
    Adjustment of cooling-water flow should not rely on the flap flow meter but on opening valve of each valve (flap flow meters used as reference only).
D05F (unclear)
  In the investigation, the vacuum-pressure rise could not be reproduced.
  D05F cavity passed all the tests conducted in this summer shutdown.
  Suggested scenario of pressure rise:
    On the maintenance day when the water leak was found, the cooling channel concerned was tentatively closed to fix the water leak.
    After the work, they forgot to re-open the cooling channel? ← No confirmation
      The cooling channel is for the movable frequency tuner of the storage cavity.
      The tuning plunger would be very hot during high-power operation, leading to vacuum-pressure rise.
D05-A and -F cavities are normal and will return to operation without cavity replacement.
→ This will contribute to higher beam current!

## Slide 31: Frequency of beam aborts caused by SBL/Beam losses
K. Uno