## Slide 1: Status of the ESS
Plans for operation and impact of COVID
PRESENTED BY Marc Munoz, on behalf of the ESS Team

## Slide 2: Agenda
1 ESS status
2 Impact of COVID
3 Creating the Operations organization
4 Conditioning and Commissioning

## Slide 3
1
ESS Status

## Slide 4: ESS at a Glance

## Slide 5: ESS Site

## Slide 6: Next steps: Installation and Commissioning

## Slide 7
Impact of COVID
2

## Slide 8: COVID development in Sweden
Chart: COVID in Sweden
Source Johns Hopkins University

## Slide 9: ESS during COVID
Start of the pandemic
Even if the external image of Sweden was that there were not many restrictive measures during COVID, that is not the reality
ESS adopted measures beyond the Swedish government recommendations
Our region (Skane) had a relatively low incidence the last two waves

## Slide 10
Work from Home was implemented the 15/3/2020:
  Only installation work at the ESS site
  TS2 Operation on site
  Cryo operation on site
Mask on site
Travels to and from ESS were severely restricted
Limited occupancy of the Local Control Room
Skanska kept working on the site the whole pandemic
After summer 2020 very limited work at the offices and labs was allowed for some groups
Mask on site and office
Occasional COVID test after vacation
Increased in the rate of installation work
Still, not travel from/to ESS
TS2 and Cryo Operation on site
ESS staff moved to the finished ESS office building and labs
Increased in the rate of installation work
Finished installation of the RFQ with help from CEA
RFQ conditioning
Creation of a second Local Control Room to conduct conditioning and commissioning
Increased occupancy, but still limited
Mask usage reduced
Start to ease the visit requirements
Weekly COVID test
29 Sept 2021 Swedish government lift restrictions (still recommendations)
15 October 50% occupancy
How all this affect the schedule?

## Slide 11: COVID cases at ESS - 2021
The total number includes ESS employees and consultants (working on ESS premises or from home), and everybody working on ESS premises: In-Kind partners, Skanska, contractors

## Slide 12: NCL plan pre-COVID (Rev. Dec 2019)
2020
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Start of RFQ Conditioning
SRR2A
Start of Beam Commissioning
SRR2B
RFQ Conditioning
4 wks
SRR2A Follow-Up
2 wks
Beam Commissioning to the MEBT FC
9 wks
PSS1 Re-Validation
3 wks
DTL1 and MEBT Bunchers Conditioning
4 wks
SRR2B Follow-Up
2 wks
Beam Commissioning to the DTL1 FC
6 wks

## Slide 13: NCL plan today
2021
2023
RFQ
MEBT
DTL
Commissioning
ISrc/LEBT
Aug
Oct
Dec
MEBT Local Hardware Tests
DTL1 Installation
DTL1 Local/Integrated Testing
Feb
Apr
Jun
2021
2022
MEBT Integrated Hardware Tests
MEBT SAR
Oct 13 '21 - Dec 17 '21
Beam Commissioning (ISrc to MEBT FC)
Jan 27 '22 - Feb 9 '22
MEBT Bunchers Conditioning
Apr 8 '22 - May 23 '22
Beam Commissioning (ISrc to DTL1 FC)
DTL2 Local/Integrated Testing
Jan 26 '23 - May 2 '23
Beam Commissioning (ISrc to DTL4)
DTL3 Local/Integrated Testing
DTL4 Local/Integrated Testing
MEBT SAR Follow-Up
ISrc/LEBT Local/Integrated Testing
ISrc/LEBT SAR Follow-Up
DTL2 Installation
Nov 2 '22 - Dec 20 '22
DTL2 Conditioning
DTL3 Installation
DTL4 Installation
Nov 2 '22 - Dec 20 '22
DTL3 Conditioning
Oct 27 '22 - Dec 14 '22
DTL4 Conditioning
ISrc/LEBT SAR
RFQ SAR
Aug
RFQ SAR Follow-Up
Feb 25 '22 - Mar 24 '22
DTL1 Conditioning
2023
Oct
Dec
Feb
Apr
Today
SRR2A
SRR2B
SRR3
Mar 18 '22
Jan 12 '23

## Slide 14: Beam on Target Situation
RBOT before COVID March 2022
RBOT after COVID March 2024 (guess as today, we are finishing a rebaselining this month)

## Slide 15: What are the reasons for the delay?
How ESS adapted to work in COVID times
Effect on InKind partners
  Delay in the installation
    I.N.F.N. Staff were not permited to travel to ESS for installation and tuning of the DTL until 8 month after the scheduled date (and tuning and installation by Facetime proved a bit difficult, but we did manage installation of 6 out of 24 post-couplers during this period)
    CEA Saclay staff also have to wait a long time before being able to come to ESS to validate RFQ installation and start the RF conditioning
  Effect on the partner labs themselves
    Reduced or completely stop of work
    Deliveries

## Slide 16
3
Creating the Operations organization

## Slide 17: Operations team
3 Shift Leaders (Arek, Benjamin, Joe) and 2 Operators (Julien) hired
2 more Shift Leaders being recruited now
Extra Temporary Operators ‘’loaned’’ by Software and Beam Physics
Training provided for operations personal, plus new learning platform (sabacloud)
During non-operation time, we have SL on site (not necessarily at the LCO) during normal working hours
Next commissioning run:
  2 shifts per day
  7 days a week
  1 SL (from Operations), 1 Operator (Ops or temporary) plus up to 6 person from predefined teams
  Limit for the moment of 8+1 persons at the LCO

## Slide 18: LCO

## Slide 19: MCR

## Slide 20: Moving ESS from Project to Operational
Always one SL on shift during working hours
Parts of the tunnel are now under PSS control, limiting the number of people in it
Daily coordination meeting run by the SL over Zoom to coordinate access to the controlled area
  Requires Work Order system working and in use
New systems ready to move to operations:
  Training system, including certification
  Identity management, linked to the training system, PSS and access
  EAM tool much improved (ESS Enterprise Asset Management System)
Better definition on the procedures and process
  Better definition of the steps before starting test on the control room (Technical and Safety reviews)
  Access to the PSS controlled area

## Slide 21
4
Conditioning and Commissioning

## Slide 22: Summary of RF conditioning
2 Shifts per day
1 SL + RFQ experts + CEA partners (at the start)
Driven by the RFQ experts
  SL to help and to operate the PSS1
Started 7 days/week, moved later to 5 days/week
RFQ conditioning to nominal (or close to nominal) field in ~650 hours of operation

## Slide 23: Commissioning restarts in one week
2 Shifts per day
Responsibilities, handover of systems
Updates in the tools:
  New logbook -> Olog
  New CS-Studio -> Phoebus version
Better prepared than the last times:
  Clearly defined stages
  Larger operation group

## Slide 24: Shift Scheduler
Web based tool
All shifts for the next commissioning run planned

## Slide 25
Backup Slides

## Slide 26: Financing: Cash and InKind

## Slide 27: RFQ Conditioning
The ESS RFQ in numbers
  2 coaxial power couplers
  4 vanes ;-)
  4.6 m long
  5 segments
  22 field pickups
  60 static tuners
  66 cooling circuits
  80-120 kV intervane voltage
  352.21 MHz
Later History:
  January – April 2018: Couplers conditioned at CEA
  August – December 2019: Installation and tuning at ESS
  June – July 2021: Conditioning

## Slide 28: Issues… (expected and unexpected)
Lack of waveform archiving: we have almost no waveform data from normal pulses
Lack of discipline with acquisition windows
  Set for a 50 µs pulse, conditioned with 25 µs…
  Lot of changes for measurement, calibration, …
Archiver was not entirely stable: multiple downtimes
LLRF stability problems
  Firmware hangs after interlocks: issue specific to RFQ system (40 acquisition channels)
Cooling water in the gallery: any valve opened/closed on the CWM circuit will affect all others
  Downtime due to klystron water flow interlocks

## Slide 29: TestStands Activity
TS2 keep working all along the pandemia
Fully qualify the first two cryostats (including the RF part) of the Medium Beta section
Success both on the cryo part and in the RF part